## Sprint Backlog
Sprint backlog:
New effort estimates
Remaining at the end
Of the day
(Each effort estimate point covers 5-day span))
Product Backlog Item | Sprint task | Volunteer | Initial estimate | 1 | 2 | 3 | 4 | 5 | Total
Coming up with new software Product | Pondering over upcoming technologies | The entire team | 4 | 4 | 0 | 0 | 0 | 0 | 4
| Thinking over market interests | Priyanka Sharma | 2 | 1 | 1 | 0 | 0 | 0 | 2
| Collection available projects | Pavan | 3 | 2 | 2 | 0 | 0 | 0 | 4
| Proposing the new project to the sponsor | Pavan and Priyanka Sharma | 5 | 2 | 3 | 0 | 0 | 0 | 5
Selecting the Product Name | Understanding the product to be built | Jai Santosh Mandava and Priyanka Sriramshetty | 5 | 1 | 2 | 2 | 0 | 0 | 5
| Contemplating innovative names | Jai Santosh Mandava | 3 | 0 | 1 | 0 | 0 | 2 | 3
| Making sure the name is unique | Manjushree | 2 | 0 | 1 | 1 | 0 | 0 | 2
| Making sure the similar name is not copyrighted | Parijat and Rani | 3 | 1 | 0 | 0 | 0 | 2 | 3
| Proposing the product name | Jai Santosh Mandava | 3 | 3 | 1 | 0 | 0 | 0 | 4
| Finalizing the product name | The entire team | 2 | 2 | 0 | 0 | 0 | 0 | 2
State the project vision | Understanding the customer needs | The entire team | 5 | 3 | 2 | 0 | 0 | 0 | 5
| Understanding the business requirements | The entire team | 4 | 1 | 1 | 2 | 0 | 0 | 4
| Understanding what has to be delivered | The entire team | 5 | 3 | 1 | 0 | 0 | 0 | 4
| Conveying ideas to the team | Pavan | 5 | 2 | 3 | 0 | 0 | 0 | 5
| State the vision | Pavan | 5 | 2 | 1 | 0 | 0 | 0 | 3
Creation of cover art, brand and logo | Collection of design options | Priyanka Sharma | 3 | 0 | 0 | 0 | 1 | 1 | 2
| Finalizing the logo | Pavan | 3 | 1 | 1 | 1 | 1 | 0 | 4
| Cover art review | Priyanka Sharma, Pavan | 2 | 2 | 0 | 0 | 0 | 0 | 2
Work on creating the sales pitch including the key selling points for the product | Understanding the project vision | Priyanka Sharma | 5 | 2 | 1 | 1 | 0 | 0 | 4
| Knowing the key features | Manjushree | 4 | 1 | 1 | 1 | 1 | 0 | 4
| Understand the selling points for business | Rani | 4 | 0 | 2 | 1 | 0 | 0 | 3
| Deciding upon the sales pitch | Yashaswini | 3 | 1 | 1 | 1 | 0 | 1 | 4
Making the concept of operations and making the system block diagram | Understand the scope | Rani | 5 | 0 | 3 | 0 | 0 | 2 | 5
| Design the concept of operations | Majushree, Santosh | 5 | 0 | 0 | 1 | 1 | 3 | 5
| Understanding each point thoroughly | Parijat, Yashaswini | 5 | 0 | 0 | 0 | 2 | 3 | 5
| Making the block diagram | Parijat, Pavan, Rani | 4 | 0 | 0 | 0 | 2 | 2 | 4
| Verifying the system block diagram | Priyanka Sharma, Manjushree | 4 | 0 | 0 | 0 | 2 | 2 | 4
Provide details on the major features/ capabilities of the new software product | Listing major capabilities | Pavan | 4 | 0 | 0 | 0 | 3 | 1 | 4
| Listing major capabilities | Manjushree | 4 | 1 | 1 | 2 | 0 | 0 | 4
| Finding details | Priyanka Sharma | 3 | 0 | 0 | 0 | 3 | 0 | 3
Creating the physical view/implementation of the product | Initiate physical implementation of the product | Team | 5 | 0 | 0 | 1 | 2 | 1 | 4
| Dividing the tasks among the development team | Pavan | 3 | 0 | 0 | 0 | 2 | 0 | 2
| (Voluntarily) | [7 empty] | 0
| Ensuring the quality | Priyanka Sriramshetty, Parijat | 3 | 0 | 0 | 0 | 3 | 0 | 3
| Ensuring the security | Santosh, Yashaswini | 4 | 0 | 0 | 1 | 2 | 1 | 4
| Ensuring the maintenance | Pavan, Rani | 5 | 0 | 1 | 1 | 0 | 2 | 4
Making the warranty policy with prices and a logistic maintenance plan | Knowing the business policies | Parijat | 3 | 0 | 0 | 1 | 2 | 0 | 3
| Make warranty policies accordingly | Rani, Parijat, Priyanka Sriramshetty | 2 | 0 | 0 | 0 | 1 | 1 | 2
| Knowing prices and logistics | Pavan, Yashaswini | 2 | 0 | 0 | 0 | 2 | 2 | 4
| Deciding upon the maintenance plan | Manjushree, Rani | 4 | 0 | 0 | 2 | 2 | 0 | 4
Providing the contact information | Divide the expected queries/problems into several categories | Santosh, Yashaswini | 3 | 0 | 2 | 0 | 0 | 0 | 2
| Based on that, list out the contact persons | Priyanka Sharma | 2 | 0 | 0 | 2 | 2 | 0 | 4
| Create the contact list | Priyanka Sriramshetty | 2 | 0 | 2 | 2 | 0 | 0 | 4
| Provide the contact information | Priyanka Sharma | 2 | 0 | 0 | 0 | 0 | 2 | 2
|  | Total | 154 | 35 | 34 | 23 | 34 | 28 | 154

## Burn Down Chart
Date . | Target. | Actual
1 | 154 | 154
2 | 115 | 119
3 | 76 | 85
4 | 39 | 28
5 | 0 | 0