## Sheet1
Sprint Retrospective
What went Right? | What went Wrong ? | How things can be Improved?
Able to finish tasks in given time | Sprint period was too long | Planning to reduce sprint to 2 weeks
Peer program | Some tasks were under estimated | Team memebers to decide the estimated value before hand
Enough time for analysis was given | Need to reduce rework by reusing documents | Aggregation of similar work to reduce rework
Shorter scrum meeting(15mins) was effective | Need a mid sprint review | May not be needed as sprint period is reduced to 2 weeks.