## Sprint Backlog
Sprint Review:
Product Backlog Item | Sprint task | Volunteer | Initial estimate | 1 | 2 | 3 | 4 | 5 | Total | Review | Comments
Coming up with new software Product | Pondering over upcoming technologies | The entire team | 4 | 4 | 0 | 0 | 0 | 0 | 4 | Accepted
| Thinking over market interests | Priyanka Sharma | 2 | 1 | 1 | 0 | 0 | 0 | 2 | Accepted
| Collection available projects | Pavan | 3 | 2 | 2 | 0 | 0 | 0 | 4 | Accepted
| Proposing the new project to the sponsor | Pavan and Priyanka Sharma | 5 | 2 | 3 | 0 | 0 | 0 | 5 | Accepted
Selecting the Product Name | Understanding the product to be built | Jai Santosh Mandava and Priyanka Sriramshetty | 5 | 1 | 2 | 2 | 0 | 0 | 5 | Accepted
| Contemplating innovative names | Jai Santosh Mandava | 3 | 0 | 1 | 0 | 0 | 2 | 3 | Accepted
| Making sure the name is unique | Manjushree | 2 | 0 | 1 | 1 | 0 | 0 | 2 | Accepted
| Making sure the similar name is not copyrighted | Parijat and Rani | 3 | 1 | 0 | 0 | 0 | 2 | 3 | Accepted
| Proposing the product name | Jai Santosh Mandava | 3 | 3 | 1 | 0 | 0 | 0 | 4 | Accepted
| Finalizing the product name | The entire team | 2 | 2 | 0 | 0 | 0 | 0 | 2 | Accepted
State the project vision | Understanding the customer needs | The entire team | 5 | 3 | 2 | 0 | 0 | 0 | 5 | Accepted
| Understanding the business requirements | The entire team | 4 | 1 | 1 | 2 | 0 | 0 | 4 | Accepted
| Understanding what has to be delivered | The entire team | 5 | 3 | 1 | 0 | 0 | 0 | 4 | Accepted
| Conveying ideas to the team | Pavan | 5 | 2 | 3 | 0 | 0 | 0 | 5 | Accepted
| State the vision | Pavan | 5 | 2 | 1 | 0 | 0 | 0 | 3 | Accepted
Creation of cover art, brand and logo | Collection of design options | Priyanka Sharma | 3 | 0 | 0 | 0 | 1 | 1 | 2 | Accepted
| Finalizing the logo | Pavan | 3 | 1 | 1 | 1 | 1 | 0 | 4 | Accepted
| Cover art review | Priyanka Sharma, Pavan | 2 | 2 | 0 | 0 | 0 | 0 | 2 | Accepted
Work on creating the sales pitch including the key selling points for the product | Understanding the project vision | Priyanka Sharma | 5 | 2 | 1 | 1 | 0 | 0 | 4 | Accepted
| Knowing the key features | Manjushree | 4 | 1 | 1 | 1 | 1 | 0 | 4 | Accepted
| Understand the selling points for business | Rani | 4 | 0 | 2 | 1 | 0 | 0 | 3 | Accepted
| Deciding upon the sales pitch | Yashaswini | 3 | 1 | 1 | 1 | 0 | 1 | 4 | Accepted
Making the concept of operations and making the system block diagram | Understand the scope | Rani | 5 | 0 | 3 | 0 | 0 | 2 | 5 | Accepted
| Design the concept of operations | Majushree, Santosh | 5 | 0 | 0 | 1 | 1 | 3 | 5 | Accepted
| Understanding each point thoroughly | Parijat, Yashaswini | 5 | 0 | 0 | 0 | 2 | 3 | 5 | Accepted
| Making the block diagram | Parijat, Pavan, Rani | 4 | 0 | 0 | 0 | 2 | 2 | 4 | Accepted
| Verifying the system block diagram | Priyanka Sharma, Manjushree | 4 | 0 | 0 | 0 | 2 | 2 | 4 | Accepted
Provide details on the major features/ capabilities of the new software product | Listing major capabilities | Pavan | 4 | 0 | 0 | 0 | 3 | 1 | 4 | Accepted
| Listing major capabilities | Manjushree | 4 | 1 | 1 | 2 | 0 | 0 | 4 | Accepted
| Finding details | Priyanka Sharma | 3 | 0 | 0 | 0 | 3 | 0 | 3 | Accepted
Creating the physical view/implementation of the product | Initiate physical implementation of the product | Team | 5 | 0 | 0 | 1 | 2 | 1 | 4 | Accepted
| Dividing the tasks among the development team | Pavan | 3 | 0 | 0 | 0 | 2 | 0 | 2 | Accepted
| (Voluntarily) | [7 empty] | 0 | Accepted
| Ensuring the quality | Priyanka Sriramshetty, Parijat | 3 | 0 | 0 | 0 | 3 | 0 | 3 | Accepted
| Ensuring the security | Santosh, Yashaswini | 4 | 0 | 0 | 1 | 2 | 1 | 4 | Accepted
| Ensuring the maintenance | Pavan, Rani | 5 | 0 | 1 | 1 | 0 | 2 | 4 | Accepted
Making the warranty policy with prices and a logistic maintenance plan | Knowing the business policies | Parijat | 3 | 0 | 0 | 1 | 2 | 0 | 3 | Accepted
| Make warranty policies accordingly | Rani, Parijat, Priyanka Sriramshetty | 2 | 0 | 0 | 0 | 1 | 1 | 2 | Accepted
| Knowing prices and logistics | Pavan, Yashaswini | 2 | 0 | 0 | 0 | 2 | 2 | 4 | Accepted
| Deciding upon the maintenance plan | Manjushree, Rani | 4 | 0 | 0 | 2 | 2 | 0 | 4 | Accepted
Providing the contact information | Divide the expected queries/problems into several categories | Santosh, Yashaswini | 3 | 0 | 2 | 0 | 0 | 0 | 2 | Accepted with exceptions | Some problems were wrongly aggregated. Accepted since there is no ambiguity.
| Based on that, list out the contact persons | Priyanka Sharma | 2 | 0 | 0 | 2 | 2 | 0 | 4 | Accepted | Took more time
| Create the contact list | Priyanka Sriramshetty | 2 | 0 | 2 | 2 | 0 | 0 | 4 | Accepted | Took more time
| Provide the contact information | Priyanka Sharma | 2 | 0 | 0 | 0 | 0 | 2 | 2 | Accepted
|  | Total | 154 | 35 | 34 | 23 | 34 | 28 | 154

## Burn Down Chart
Date . | Target. | Actual
1 | 154 | 154
2 | 115 | 119
3 | 76 | 85
4 | 39 | 28
5 | 0 | 0